Project Planning ShopEZ — MERN Stack E-commerce Application Phase: Project Planning Phase TEAM ID : SWUID2026207177 Classification: Project Documentation — For Academic Submission

Project Planning

1

. Introduction

This document formalises the project planning artefacts for the ShopEZ development initiative. It encompasses the Product Backlog, Sprint Schedule with Story Point estimates, a Sprint Timeline (Gantt Chart), Velocity Tracking, Burndown Analysis, and a Risk Register. The planning framework adopted is Scrum-based Agile, executed in three two-week sprints.

| Sprint 1 | Project Setup & DB | USN- 0 | Initialise React | 3 | High |
| --- | --- | --- | --- | --- | --- |

# 2. Product Backlog & Sprint Schedule

| Sprint | Epic | USN | User Story / Task | Points | Priority |
| --- | --- | --- | --- | --- | --- |

frontend, Node.js backend, and configure

MongoDB

Atlas models

| Sprint 1 | User Auth | USN- 1 | User can register with email, name, and password and receive a JWT session | 2 | High |
| --- | --- | --- | --- | --- | --- |

Sprint	User Auth	USN-	User can	2	High

- 2	log in with

credentials and be granted a JWT in an

HTTP-only

cookie

Sprint

1

Product

Catalogue

USN

-

3

Admin

can

create

,

edit

,

and

delete

product

listings

with

Cloudinary

3

High

| Sprint | Epic | USN | User Story / Task | Points | Priority |
| --- | --- | --- | --- | --- | --- |
|  |  |  | image uploads |  |  |

Sprint	Shopping	USN-	User can	3	High

- Cart	4	add, update,

and remove items; cart persists across devices

| Sprint 2 | Checkout Flow | USN- 5 | User can complete a 3-step checkout (Address → Payment Method → Confirm Order) | 3 | High |
| --- | --- | --- | --- | --- | --- |

Sprint	Payment	USN-	User can	5	High

- 6	pay via

Stripe / Razorpay and receive order confirmation

| Sprint 3 | Order Management | USN- 7 | Admin can view all orders and update delivery status | 2 | Medium |
| --- | --- | --- | --- | --- | --- |

Sprint	Reviews	USN-	User can	2	Medium

- 8	leave a star

rating and

| Sprint | Epic | USN | User Story / Task | Points | Priority |
| --- | --- | --- | --- | --- | --- |

text review on a purchased product

| Sprint 3 | Admin Dashboard | USN- 9 | Admin can view monthly revenue charts and sales metric summaries | 3 | Medium |
| --- | --- | --- | --- | --- | --- |

# 3. Sprint Timeline — Gantt Chart

2026-06-07

2026-06-14

2026-06-21

2026-06-28

2026-07-05

2026-07-12

Project Setup and MongoDB Config

User Authentication (Register & Login)

Product Catalogue (CRUD + Cloudinary)

Shopping Cart (Persist + CRUD)

Multi-Step Checkout Flow

Payment Gateway Integration

Admin

Order

Management

Product

Reviews

and

Ratings

Admin

Sales

Dashboard

Sprint 1 — Foundation

Sprint 2 — Core Commerce

Sprint 3 — Operations

ShopEZ Sprint Delivery Timeline

F

I

G

U

R

E

3

.

1

—

G

A

N

T

T

C

H

A

R

T

:

S

P

R

I

N

T

D

E

L

I

V

E

R

Y

T

I

M

E

L

I

N

E

(

3

S

P

R

I

N

T

S

×

2

W

E

E

K

S

)

# 4. Velocity & Project Tracker

| Sprint | Story Points | Start Date | End Date | Completed | Rate |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | 10 | 01 June 2026 | 14 June 2026 | 10 | 100% ✅ |
| Sprint 2 | 11 | 15 June 2026 | 28 June 2026 | 11 | 100% ✅ |
| Sprint 3 | 7 | 29 June 2026 | 12 July 2026 | 7 | 100% ✅ |
| Total | 28 | — | — | 28 | 100% ✅ |

Average Velocity: 9.3 Story Points per Sprint | Sprint Duration: 2 Weeks

# 5. Risk Register

| Risk ID |  | Risk Description | Probability | Impact | Mitigation Strategy |  |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Payment gateway API downtime during testing | Medium | High | Use Stripe test mode ( sk_test_* ); maintain fallback |

mock handler

| R- 02 |  | MongoDB Atlas connection failure in production | Low | High | Configure automatic reconnect logic; monitor via Atlas alerts |  |
| --- | --- | --- | --- | --- | --- | --- |
| R- 03 | Cloudinary storage limit exceeded | Low | Medium | Set file size limits in upload middleware; configure usage |

alerts

| R- 04 |  | JWT secret key exposed via public repository | Low | Critical | Store all secrets in .env (gitignored); enforce secret scanning |  |
| --- | --- | --- | --- | --- | --- | --- |
| R- 05 | Cart state desync on concurrent multi-device login | Medium | Medium | Server-side cart reconciliation on login; use updatedAt timestamps |
| R- 06 |  | React build size impacting initial load time | Medium | Medium | Implement React.lazy() code-splitting; enable Gzip on server |  |

# 6. Conclusion

The Agile sprint framework provided the V S S S Manikanta with a structured, iterative approach to delivery. All 28 story points were completed within the planned six-week timeline, with a 100% completion rate across all three sprints.

ShopEZ MERN E-commerce Application · Project Planning Phase · Project Planning ·